## Project To do
Category | Sub-Category | Task | Time | Priority | Status | Commets | Status Enums
Homepage | General | Add Fields | 1:30 | High | Done |  | Done
|  | Listview of fields | 1:30 | High | Done |  | In progress
|  | Listview has link to each detailed view | 1:30 | High | Done |  | To do
|  | Map with locations | 6:00 | High | Done
| Navbar | Logo | 1:00 | High | Done |  | Priority Enums
|  | Fields link |  | High | Done |  | High
|  | Add Fields link | 2:00 | High | Done |  | Medium
| Searchbar | Sort by city | 3:00 | High | Done |  | Low
|  | Sort by sport | 2:00 | Low | To do
|  | Search button functionality | 2:00 | Medium | To do
Detailed View | General | Map + location | 4:00 | High | Done
|  | Name, adress, directions, price, opening hours | 2:00 | High | In progress
| Non-user | Form to request field according to data and time - send email to me in order to help schedule a time | 3:00 | High | To do
| Is-User | LIVE! Schedule to book a field | 12:00 | Medium | To do
|  | Pay for the field when ordering | 20:00 | Low | To do
Add Field | General | Contact form to request to add field (may include signup to service) | 3:00 | Medium | To do
|  | Submit contact form to my email |  | Medium | To do
Sign in / up | General | Sign-in page | 2:00 | Low | To do
|  | Sign-in/up logic | 6:00 | Low | To do
|  | Sign-up form (maybe create user once adding a field) |  | Low | To do
User schedule view | General | Schedule where user can add booking by himself + add according to field ordering | 12:00 | Medium | To do